## Project Management Data
Budget | Country (Geo) | End Date | Expense | FALSE | Location1 | Overall Project Health | Planned Date | Priority | Project ID | Project Manager | Project Name | Project Schedule | Project Type | Start Date | Status | % Complete | Priority1
$2,000 | Nigeria | 2019-12-10 | 0 | FALSE | Uyo | On Track | 2019-10-25 | Medium | 1 | Dave Chieke | Auditorium Setup 1 | 242 | Building Construction | 2019-12-02 | In Progress | 0.93 | 3
$20,000 | Nigeria | 2020-04-10 | 19800 | FALSE | Kano | On Track | 2020-04-20 | Very Low | 2 | Ema Ekpo | Lab Implementation 1 | 430 | Building Construction | 2019-05-02 | In Progress | 0.95 | 1
$8,700 | Nigeria | 2020-03-02 | 6490 | FALSE | Lagos | On Track | 2020-02-03 | Very High | 3 | Ema Ekpo | Park Place 1 | 268 | Road Construction | 2019-11-05 | In Progress | 0.46 | 5
$10,000 | Nigeria | 2020-11-02 | 7540 | FALSE | Borno | On Track | 2020-02-21 | Low | 4 | Ema Ekpo | Science Park Phase 2 | 245 | Borehole & Reticulation | 2019-11-06 | In Progress | 0.59 | 2
$7,000 | Nigeria | 2020-06-03 | 6500 | FALSE | Lagos | On Track | 2020-03-06 | Low | 5 | Ema Ekpo | Research Offices | 299 | Borehole & Reticulation | 2019-12-05 | In Progress | 0.22 | 2
$15,000 | Nigeria | 2020-01-04 | 8700 | FALSE | Sokoto | On Track | 2020-04-01 | Very High | 6 | Ema Ekpo | Innovation Classroom | 297 | Borehole & Reticulation | 2019-09-06 | On Hold | 0.61 | 5
$12,000 | Nigeria | 2020-10-04 | 13900 | FALSE | Kano | On Track | 2020-04-20 | Very Low | 7 | Ema Ekpo | Lab Implementation | 342 | Supplies | 2019-04-05 | In Progress | 0.95 | 1
$9,080 | Nigeria | 2020-03-02 | 2560 | FALSE | Lagos | On Track | 2020-02-03 | Medium | 8 | Ema Ekpo | Park Place 2 | 168 | Transformer Installation | 8/19/19 | In Progress | 0.46 | 3
$18,000 | Nigeria | 2020-09-04 | 11500 | FALSE | Kano | On Track | 2020-04-20 | High | 9 | Ema Ekpo | Lab Implementation | 254 | Transformer Installation | 7/30/19 | In Progress | 0.95 | 4
$3,400 | Nigeria | 2020-03-02 | 2300 | FALSE | Lagos | On Track | 2020-02-03 | High | 10 | Ema Ekpo | Park Place 3 | 168 | Rehabilitation | 8/19/19 | In Progress | 0.46 | 4
$63,600 | Nigeria | 2020-12-08 | 0 | FALSE | Abuja | Needs Attention | 2020-08-19 | Very Low | 11 | Dave Chieke | Lab Building Construction 1 | 179 | Building Construction | 2/15/20 | Planned | 0 | 1
$6,000 | Nigeria | 2020-06-03 | 4080 | FALSE | Lagos | On Track | 2020-03-06 | Very Low | 12 | Ema Ekpo | Research Offices | 241 | Road Construction | 2019-09-07 | In Progress | 0.22 | 1
$4,300 | Nigeria | 2020-06-03 | 4450 | FALSE | Lagos | On Track | 2020-03-06 | Medium | 13 | Ema Ekpo | Research Offices | 213 | Borehole & Reticulation | 2019-06-08 | In Progress | 0.22 | 3
$5,500 | Nigeria | 2020-06-03 | 1000 | FALSE | Lagos | On Track | 2020-03-06 | Low | 14 | Ema Ekpo | Research Offices | 249 | Rehabilitation | 2019-01-07 | In Progress | 0.22 | 2
$34,500 | Nigeria | 2019-12-10 | 30000 | FALSE | Uyo | On Track | 2019-10-25 | Low | 15 | Dave Chieke | Classroom Arrangement | 154 | Rehabilitation | 2019-11-05 | In Progress | 0.93 | 2
$7,000 | Nigeria | 2020-10-02 | 6580 | FALSE | Borno | On Track | 2020-02-21 | Very Low | 16 | Ema Ekpo | Science Park 1 | 184 | Building Construction | 2019-10-08 | In Progress | 0.59 | 1
$4,500 | Nigeria | 2020-01-10 | 0 | FALSE | Lagos | Needs Attention | 2020-10-01 | Very High | 17 | Ema Ekpo | Creative Media Industries 1 | 51 | Building Construction | 2020-11-08 | Planned | 0 | 5
$23,000 | Nigeria | 2019-12-12 | 20340 | FALSE | Kano | On Track | 2019-12-13 | Medium | 18 | Sarah Boulos | Lab Implementation | 91 | Road Construction | 2019-12-09 | In Progress | 0.35 | 3
$1,500 | Nigeria | 2019-12-07 | 980 | FALSE | Rivers | Not Set | 2019-07-26 | Very High | 19 | Dave Chieke | Central Deployment | 40 | Borehole & Reticulation | 2019-02-06 | On Hold | 0.14 | 5
$9,800 | Nigeria | 2020-12-02 | 9050 | FALSE | Borno | On Track | 2020-02-21 | Very Low | 20 | Ema Ekpo | Science Park 2 | 187 | Building Construction | 2019-09-08 | In Progress | 0.59 | 1
$23,000 | Nigeria | 2020-12-10 | 0 | FALSE | Abuja | Needs Attention | 2020-10-15 | Very High | 21 | Dave Chieke | Lab Building Construction 2 | 37 | Building Construction | 2020-05-09 | Planned | 0 | 5
$1,200 | Nigeria | 2020-12-10 | 0 | FALSE | Lagos | Needs Attention | 2020-10-18 | Very High | 22 | Ema Ekpo | Creative Media Industries 2 | 11 | Building Construction | 2020-01-10 | Planned | 0 | 5
$12,300 | Nigeria | 2019-12-12 | 15000 | FALSE | Kano | On Track | 2019-12-13 | Medium | 23 | Sarah Boulos | Classroom Arrangement 1 | 100 | Building Construction | 2019-03-09 | In Progress | 0.35 | 3
$2,340 | Nigeria | 2020-02-11 | 0 | FALSE | Abuja | Not Set | 2020-11-28 | Very Low | 24 | Dave Chieke | Classroom Arrangement | 121 | Road Construction | 2020-04-07 | Planned | 0 | 1
$1,500 | Nigeria | 2020-12-10 | 0 | FALSE | Abuja | Not Set | 2020-10-26 | Medium | 25 | Dave Chieke | Classroom Arrangement | 98 | Borehole & Reticulation | 2020-06-07 | Planned | 0 | 3
$750 | Nigeria | 2020-05-01 | 0 | FALSE | Abuja | Needs Attention | 2020-01-05 | Low | 26 | Dave Chieke | Lab Building Construction 3 | 188 | Building Construction | 2019-01-07 | Planned | 0 | 2
$45,000 | Nigeria | 2020-10-09 | 0 | FALSE | Lagos | Needs Attention | 2020-09-30 | Low | 27 | Ema Ekpo | Creative Media Industries | 68 | Transformer Installation | 2020-04-07 | Planned | 0 | 2
$1,230 | Nigeria | 2020-10-09 | 0 | FALSE | Kano | On Track | 2020-09-30 | Medium | 28 | Sarah Boulos | Classroom Arrangement 2 | 352 | Building Construction | 9/24/19 | Planned | 0 | 3
$53,855 | Nigeria | 2020-08-05 | 42560 | FALSE | Kano | On Track | 2020-05-08 | Very Low | 29 | Vivian Ade | Innovation Classroom | 165 | Transformer Installation | 11/25/19 | In Progress | 0.76 | 1
$3,500 | Nigeria | 2020-10-02 | 3560 | FALSE | Borno | On Track | 2020-02-21 | Low | 30 | Ema Ekpo | Science Park 3 | 175 | Building Construction | 8/19/19 | In Progress | 0.59 | 2
$790 | Nigeria | 2020-11-08 | 0 | FALSE | Lagos | Needs Attention | 2020-08-29 | Medium | 31 | Ema Ekpo | Creative Media Industries | 113 | Transformer Installation | 4/20/20 | Planned | 0 | 3
$10,000 | Nigeria | 2019-12-12 | 4500 | FALSE | Kano | On Track | 2019-12-13 | High | 32 | Sarah Boulos | Classroom Arrangement 3 | 90 | Building Construction | 9/13/19 | In Progress | 0.35 | 4
$2,000 | Nigeria | 2019-11-07 | 3400 | FALSE | Rivers | Not Set | 2019-07-26 | High | 33 | Dave Chieke | Central Deployment | 20 | Transformer Installation | 6/21/19 | On Hold | 0.14 | 4
$4,000 | Nigeria | 2019-12-03 | 3700 | FALSE | Borno | On Track | 2019-02-21 | Low | 34 | Ema Ekpo | Science Park 4 | 52 | Building Construction | 1/19/19 | In Progress | 0.59 | 2
$7,000 | Nigeria | 2019-12-12 | 5690 | FALSE | Uyo | On Track | 2019-10-25 | Very High | 35 | Dave Chieke | Classroom Arrangement | 195 | Transformer Installation | 5/31/19 | In Progress | 0.93 | 5
$36,000 | Nigeria | 2020-12-12 | 25350 | FALSE | Borno | On Track | 2020-12-01 | High | 36 | Ema Ekpo | Central Deployment | 277 | Road Construction | 2020-10-03 | In Progress | 0.39 | 4
$3,400 | Nigeria | 2019-12-11 | 3100 | FALSE | Abuja | On Track | 2019-11-20 | High | 37 | Ema Ekpo | External Wi-Fi Expansion | 171 | Borehole & Reticulation | 5/25/19 | In Progress | 0.89 | 4
$4,560 | Nigeria | 2019-12-11 | 6510 | FALSE | Borno | On Track | 2019-11-14 | Very High | 38 | Ema Ekpo | Ticketing System | 149 | Supplies | 6/16/19 | In Progress | 0.6 | 5
$9,585 | Nigeria | 2019-12-10 | 9500 | FALSE | Uyo | On Track | 2019-10-25 | Low | 39 | Dave Chieke | Auditorium Setup 2 | 134 | Building Construction | 5/31/19 | In Progress | 0.93 | 2
$6,000 | Nigeria | 2019-12-10 | 0 | FALSE | Uyo | On Track | 2019-10-25 | Low | 40 | Dave Chieke | Auditorium Setup 3 | 134 | Building Construction | 5/31/19 | In Progress | 0.93 | 2
$1,200 | Nigeria | 2019-12-12 | 500 | FALSE | Lagos | On Track | 2019-12-17 | Very High | 41 | James Seun | External Wi-Fi Expansion | 159 | Transformer Installation | 2019-06-07 | On Hold | 0.5 | 5
$23,000 | Nigeria | 2019-12-11 | 21000 | FALSE | Borno | On Track | 2019-11-14 | Low | 42 | Ema Ekpo | Ticketing System | 149 | Transformer Installation | 6/16/19 | In Progress | 0.6 | 2
$4,000 | Nigeria | 2019-12-08 | 0 | FALSE | Uyo | On Track | 2019-11-25 | Medium | 43 | Dave Chieke | Auditorium Setup 4 | 73 | Building Construction | 5/31/19 | In Progress | 0.93 | 3
$7,000 | Nigeria | 2020-10-12 | 0 | FALSE | Lagos | Not Set | 2020-12-31 | Very Low | 44 | Ema Ekpo | Park Place 4 | 297 | Transformer Installation | 2/17/20 | Planned | 0 | 1
$16,000 | Nigeria | 2020-02-01 | 14560 | FALSE | Abuja | Needs Attention | 2020-01-02 | Very High | 45 | James Seun | Innovation Classroom | 164 | Transformer Installation | 7/22/19 | Completed | 1 | 5
$4,565 | Nigeria | 2020-03-12 | 2365 | FALSE | Lagos | Needs Attention | 2020-03-25 | Medium | 46 | Ema Ekpo | Floor Renovation 1 | 239 | Building Construction | 7/17/19 | Completed | 1 | 3
$3,400 | Nigeria | 2019-12-12 | 1240 | FALSE | Abuja | Needs Attention | 2019-11-28 | Medium | 47 | James Seun | Education Theatre 1 | 173 | Building Construction | 6/22/19 | Completed | 1 | 3
$2,300 | Nigeria | 2019-12-11 | 1760 | FALSE | Borno | On Track | 2019-11-22 | Medium | 48 | James Seun | Sculpture Building | 109 | Transformer Installation | 7/26/19 | In Progress | 0.36 | 3
$1,235 | Nigeria | 2020-12-02 | 760 | FALSE | Borno | On Track | 2020-02-21 | Medium | 49 | Ema Ekpo | Science Park 5 | 177 | Building Construction | 8/19/19 | In Progress | 0.59 | 3
$1,500 | Nigeria | 2020-12-02 | 1235 | FALSE | Lagos | Needs Attention | 2020-02-25 | High | 50 | Ema Ekpo | Creative Media Industries 3 | 156 | Building Construction | 2019-09-09 | Completed | 1 | 4
$15,000 | Nigeria | 2019-12-12 | 4355 | FALSE | Kano | On Track | 2019-12-13 | Low | 51 | Sarah Boulos | Classroom Arrangement 4 | 90 | Building Construction | 9/13/19 | In Progress | 0.35 | 2
$500 | Nigeria | 2019-12-09 | 600 | FALSE | Uyo | On Track | 2019-10-25 | Very High | 52 | Dave Chieke | Classroom Arrangement | 104 | Transformer Installation | 5/31/19 | In Progress | 0.93 | 5
$1,455 | Nigeria | 2020-12-04 | 970 | FALSE | Borno | On Track | 2020-02-21 | High | 53 | Ema Ekpo | Science Park 6 | 237 | Building Construction | 8/19/19 | In Progress | 0.59 | 4
$6,000 | Nigeria | 2020-06-03 | 5890 | FALSE | Lagos | On Track | 2020-03-06 | Very High | 54 | Ema Ekpo | Research Offices 1 | 200 | Building Construction | 8/19/19 | In Progress | 0.22 | 5
$1,235 | Nigeria | 2020-01-04 | 760 | FALSE | Sokoto | On Track | 2020-04-01 | Very Low | 55 | Ema Ekpo | Innovation Classroom | 218 | Transformer Installation | 8/27/19 | On Hold | 0.61 | 1
$1,500 | Nigeria | 2020-12-04 | 1235 | FALSE | Kano | On Track | 2020-04-20 | Medium | 56 | Ema Ekpo | Lab Implementation 2 | 275 | Building Construction | 2019-12-07 | In Progress | 0.95 | 3
$3,400 | Nigeria | 2020-12-04 | 3100 | FALSE | Lagos | Needs Attention | 2020-04-25 | Low | 57 | Ema Ekpo | Park Place 5 | 270 | Transformer Installation | 7/17/19 | Completed | 1 | 2
$2,400 | Nigeria | 2019-12-12 | 1000 | FALSE | Abuja | Not Set | 2019-11-28 | Very Low | 58 | James Seun | Education Theatre 2 | 143 | Building Construction | 7/22/19 | Completed | 1 | 1
$9,585 | Nigeria | 2020-12-03 | 9500 | FALSE | Lagos | Needs Attention | 2020-03-25 | Very Low | 59 | Ema Ekpo | Park Place 6 | 239 | Road Construction | 7/17/19 | Completed | 1 | 1
$10,000 | Nigeria | 2019-12-12 | 8600 | FALSE | Abuja | Needs Attention | 2019-12-28 | Very Low | 60 | James Seun | Innovation Classroom | 143 | Borehole & Reticulation | 7/22/19 | Completed | 1 | 1
$8,000 | Nigeria | 2020-12-03 | 6400 | FALSE | Lagos | Needs Attention | 2020-03-25 | Very Low | 61 | Ema Ekpo | Floor Renovation 2 | 239 | Building Construction | 7/17/19 | Completed | 1 | 1
$51,345 | Nigeria | 2019-10-11 | 47680 | FALSE | Kano | On Track | 2019-11-20 | Medium | 62 | Vivian Ade | Innovation Classroom | 29 | Supplies | 2019-12-10 | In Progress | 0.49 | 3
$4,300 | Nigeria | 2020-12-03 | 0 | FALSE | Borno | On Track | 2020-03-21 | High | 63 | Cinci Momoh | Science Park 7 | 213 | Building Construction | 2019-12-08 | In Progress | 0.59 | 4
$1,200 | Nigeria | 2020-06-03 | 250 | FALSE | Lagos | On Track | 2020-03-06 | Low | 64 | Cinci Momoh | Research Offices 2 | 200 | Building Construction | 8/19/19 | In Progress | 0.22 | 2
$1,340 | Nigeria | 2020-01-04 | 540 | FALSE | Sokoto | On Track | 2020-04-01 | Very Low | 65 | Cinci Momoh | Network Connectivity | 218 | Building Construction | 8/27/19 | On Hold | 0.61 | 1
$2,340 | Nigeria | 2020-12-04 | 2600 | FALSE | Kano | On Track | 2020-04-20 | Very Low | 66 | Cinci Momoh | Lab Implementation | 244 | Transformer Installation | 2019-12-08 | Cancelled | 0.95 | 1
$930 | Nigeria | 2020-12-08 | 0 | FALSE | Lagos | Needs Attention | 2020-08-25 | Very High | 67 | Cinci Momoh | Park Place 7 | 366 | Supplies | 2019-12-08 | Planned | 0 | 5
$6,000 | Nigeria | 2019-12-12 | 4300 | FALSE | Abuja | Not Set | 2019-12-28 | Very Low | 68 | James Seun | Education Theatre 3 | 143 | Building Construction | 7/22/19 | Completed | 1 | 1
$2,400 | Nigeria | 2020-12-03 | 1000 | FALSE | Lagos | Needs Attention | 2020-03-20 | Low | 69 | Cinci Momoh | Floor Renovation 3 | 239 | Building Construction | 7/17/19 | Completed | 1 | 2
$16,000 | Nigeria | 2019-12-12 | 10090 | FALSE | Abuja | Needs Attention | 2019-12-28 | Medium | 70 | James Seun | Education Theatre 4 | 143 | Building Construction | 7/22/19 | Completed | 1 | 3
$3,400 | Nigeria | 2020-12-02 | 0 | FALSE | Borno | On Track | 2020-02-21 | Medium | 71 | Cinci Momoh | Ticketing System | 184 | Road Construction | 2019-12-08 | Cancelled | 0.59 | 3
$23,000 | Nigeria | 2020-12-02 | 10590 | FALSE | Lagos | Not Set | 2020-02-25 | Very High | 72 | Abdul Rex | Park Place 8 | 187 | Borehole & Reticulation | 2019-09-08 | Completed | 1 | 5
$15,000 | Nigeria | 2019-12-12 | 5550 | FALSE | Kano | On Track | 2019-12-13 | High | 73 | Sarah Boulos | Classroom Arrangement 5 | 91 | Building Construction | 2019-12-09 | Cancelled | 0.35 | 4
$16,000 | Nigeria | 2019-12-07 | 16890 | FALSE | Rivers | Not Set | 2019-07-26 | Medium | 74 | Dave Chieke | Training Room | 63 | Building Construction | 2019-10-05 | On Hold | 0.14 | 3
$3,400 | Nigeria | 2020-10-02 | 2300 | FALSE | Borno | On Track | 2020-02-21 | Low | 75 | Abdul Rex | Ticketing System | 183 | Road Construction | 2019-11-08 | Cancelled | 0.59 | 2
$23,000 | Nigeria | 2019-12-10 | 21450 | FALSE | Abuja | Needs Attention | 2019-10-28 | Very Low | 76 | Dave Chieke | Classroom Arrangement | 29 | Borehole & Reticulation | 9/13/19 | Completed | 1 | 1
$1,500 | Nigeria | 2020-12-02 | 1340 | FALSE | Lagos | Needs Attention | 2020-02-25 | Very Low | 77 | Abdul Rex | Creative Media Industries 4 | 187 | Building Construction | 2019-09-08 | Completed | 1 | 1
$16,000 | Nigeria | 2019-11-12 | 15465 | FALSE | Kano | On Track | 2019-12-13 | Medium | 78 | Sarah Boulos | Classroom Arrangement 6 | 91 | Building Construction | 2019-11-09 | Cancelled | 0.35 | 3
$13,400 | Nigeria | 2019-12-10 | 7000 | FALSE | Abuja | Needs Attention | 2019-10-22 | Low | 79 | Dave Chieke | Classroom Arrangement | 19 | Borehole & Reticulation | 9/23/19 | Completed | 1 | 2
$23,000 | Nigeria | 2019-12-10 | 20345 | FALSE | Abuja | Not Set | 2019-02-28 | Very High | 80 | Dave Chieke | Classroom Arrangement | 19 | Supplies | 9/23/19 | Completed | 1 | 5
$10,500 | Nigeria | 2019-12-10 | 10240 | FALSE | Abuja | Needs Attention | 2019-10-12 | High | 81 | Dave Chieke | Classroom Arrangement | 19 | Road Construction | 9/23/19 | Completed | 1 | 4
$5,000 | Nigeria | 2020-12-02 | 3400 | FALSE | Lagos | Needs Attention | 2020-02-12 | Low | 82 | Abdul Rex | Park Place 9 | 187 | Borehole & Reticulation | 2019-09-08 | Completed | 1 | 2
$1,000 | Nigeria | 2020-03-07 | 0 | FALSE | Kano | On Track | 2020-12-13 | High | 83 | Sarah Boulos | Classroom Arrangement 7 | 182 | Building Construction | 2020-03-01 | Planned | 0 | 4
$63,600 | Nigeria | 2020-09-08 | 0 | FALSE | Abuja | Needs Attention | 2020-08-19 | Very Low | 84 | Dave Chieke | Lab Building Construction 1 | 182 | Building Construction | 2020-09-02 | Planned | 0 | 1
$6,000 | Nigeria | 2020-06-03 | 4080 | FALSE | Lagos | On Track | 2020-03-06 | Very Low | 85 | Abdul Rex | Research Offices | 329 | Road Construction | 2019-12-04 | In Progress | 0.22 | 1
$4,300 | Nigeria | 2020-06-03 | 4450 | FALSE | Lagos | On Track | 2020-03-06 | Medium | 86 | Abdul Rex | Research Offices | 269 | Borehole & Reticulation | 2019-11-06 | In Progress | 0.22 | 3
$5,500 | Nigeria | 2020-06-03 | 1000 | FALSE | Lagos | On Track | 2020-03-06 | Low | 87 | Abdul Rex | Research Offices | 262 | Rehabilitation | 6/18/19 | In Progress | 0.22 | 2
$34,500 | Nigeria | 2019-11-10 | 30000 | FALSE | Uyo | On Track | 2019-10-25 | Low | 88 | Dave Chieke | Classroom Arrangement | 214 | Rehabilitation | 2019-11-03 | In Progress | 0.93 | 2
$7,000 | Nigeria | 2020-01-02 | 6580 | FALSE | Borno | On Track | 2020-02-21 | Very Low | 89 | Abdul Rex | Science Park 1 | 295 | Building Construction | 2019-12-04 | In Progress | 0.59 | 1
$4,500 | Nigeria | 2020-01-10 | 0 | FALSE | Lagos | Needs Attention | 2020-10-01 | Very High | 90 | Abdul Rex | Creative Media Industries 1 | 143 | Building Construction | 2020-11-05 | Planned | 0 | 5
$23,000 | Nigeria | 2019-11-10 | 20340 | FALSE | Kano | On Track | 2019-12-13 | Medium | 91 | Sarah Boulos | Lab Implementation | 154 | Road Construction | 2019-10-05 | In Progress | 0.35 | 3
$1,500 | Nigeria | 2019-12-05 | 980 | FALSE | Rivers | Not Set | 2019-07-26 | Very High | 92 | Vivian Ade | Central Deployment | 30 | Borehole & Reticulation | 2019-12-04 | On Hold | 0.14 | 5
$9,800 | Nigeria | 2020-11-04 | 9050 | FALSE | Borno | On Track | 2020-02-21 | Very Low | 93 | Abdul Rex | Science Park 2 | 276 | Building Construction | 2019-10-07 | In Progress | 0.59 | 1
$23,000 | Nigeria | 2020-05-12 | 0 | FALSE | Abuja | Needs Attention | 2020-10-15 | Very High | 94 | Vivian Ade | Lab Building Construction 2 | 81 | Building Construction | 9/15/20 | Planned | 0 | 5
$1,200 | Nigeria | 2020-10-12 | 0 | FALSE | Lagos | Needs Attention | 2020-10-18 | Very High | 95 | Abdul Rex | Creative Media Industries 2 | 192 | Building Construction | 2020-01-06 | Planned | 0 | 5
$12,300 | Nigeria | 2019-12-12 | 15000 | FALSE | Kano | On Track | 2019-12-13 | Medium | 96 | Cinci Momoh | Classroom Arrangement 1 | 93 | Building Construction | 2019-10-09 | In Progress | 0.35 | 3
$2,340 | Nigeria | 2020-02-04 | 0 | FALSE | Abuja | Not Set | 2020-11-28 | Very Low | 97 | Vivian Ade | Classroom Arrangement | 89 | Road Construction | 2020-04-01 | Planned | 0 | 1